MST Project 2021

Project Initiation Document

Company Name:

# Address:

Telephone Number:

Website:

Name of assigned company contact:

Position:

Telephone:

Mobile:

Email:

Project team:

| Name | Email | Mobile |
| --- | --- | --- |

Project title:	Office of the future

Understand what future offices need to look like to continue as a successful company? 

Section 1: Background
Summary of reasons for client interest in this project/why it is significant

Statement of key research question(s) and key issues

Exploiting cloud based mobile IT system

Has a range of advantages

Wish to counter any disadvantages

Section 2: Project Definition
Objectives

The objective of this project is to provide insights into how our client can restructure its working practices to create an “office for the future”, through developing a people-based framework rooted in staff needs. Key considerations will be staff needs for desk and collaboration space, the maintenance of organizational culture, and ensuring staff efficiency, safety, and well-being.

The framework used will factor in the dynamics of Covid-19, and should be modifiable to the different business units of Mott MacDonald, though its focus is the Water and Environment unit. 

Deliverables (presentation, including target audience)

The key deliverable is a presentation of ideas to senior staff in the Water and Environment unit, as well as potentially senior executives from other business units. (Do we want to include a written handout? Unsure what else to say here lol)

Method of approach (data/contacts/sample frame/information resources/ quantitative-qualitative mix)

The method of approach will be to draw upon a range of academic literature, with a focus on applying relevant concepts to the dynamics of the Water and Environment unit. Our understanding of these needs will be developed through focus group interviews with a range of staff.

As such, our approach is largely qualitative, extracting key data from focus group interviews and academic literature. However, quantitative data will no doubt be used to augment our analyses. These will be gained from previous studies on relevant topics, as well as key information about the firm itself.

Scope

The scope of this project is the specific needs of the Water and Environment unit. General principles may remain applicable to other business units, and some insight will be provided on this, but nevertheless the focus of our analyses will be the Water and Environment unit only.

By extension, the project is mainly focused on workers in the Cambridgeshire region, where the Water and Environment unit’s employees are clustered.

Constraints

Productivity and other performance metrics will not be supplied to support our analysis, though we will be able to extract subjective measures from employees during our focus group interviews. We will remain acutely aware that the confidence intervals for these measures will be broad, and will factor this into our conclusions.

Another constraint relates our focus groups. The nature of online meetings, coupled with time constraints, means we will not be able to interview all members of the Water and Environment unit. We will take measures to ensure we interview a sufficient breadth and diversity of employees, to add sufficient weight to our findings. 

Exclusions

Our client has specified that they are not seeking suggestions on actual configurations of furniture and resources, i.e., floor plans. Rather, they are looking for the benefits and disbenefits of a range of possibilities, and general recommendations supported by theory and data.

Further, the analysis is based on local conditions and dynamics, and is not to be extrapolated to speculate on the firm’s overseas offices. This is because due to operational and cultural heterogeneity, the conclusions we gather in our focus groups may not hold for overseas employees.

Interfaces (how the project fits into overall organisation management - and relationships with partners)

This project has wider implications for the overall organization management because many of the ingredients used to formulate an office for the future will be shared across business units.

Further, the project has significance to partners, whether suppliers or customers, as for example the optimization of working patterns and procedures can have direct impacts on staff wellbeing and productivity, thus the experience of Mott MacDonald’s customers.

Assumptions (e.g. expected input from the client, expected location of work)

The expected location of work is remote, i.e., online. It is likely that the presentation of deliverables will also occur virtually.

The client has agreed to provide us with information on a similar study previously conducted by its own employees – the Sapphire project. This will serve as a useful starting point for our research. The client has also outlined the factors it wishes us to consider when assessing how it should construct its offices for the future.

A further expected input from the client is the opportunity to interview employees in our focus groups, as well as assistance in creating and running these interviews, potentially through moderator-type assistance.

Section 3: Project organisation structure
Key roles, key client sponsor(s), key contact points, reporting structure

- Mark

- Emails twice a week

Section 4: Initial, high-level Project Plan/GANTT chart
Assignments (tasks)

- Company research, focus groups

- Literature review and solution formation

- Run past focus groups

- Adapt recommendations

- Form presentation 

Timings

Section 5: Anticipated Expenses

There are no anticipated expenses, although it is possible that certain academic articles of interest may require purchase or rental.

Section 6: Quality review procedure (review meetings)
Type here

Section 7: Risks
Type here

Signed on behalf of project team:

| Name | Signature | Date |
| --- | --- | --- |

Signed on behalf of academic supervisor:

| Name | Signature | Date |
| --- | --- | --- |

Signed on behalf of host company:

| Name | Signature | Date |
| --- | --- | --- |

Do 2 and 5 -

Sal – technical excellence lead in water and environment division.

Tamzin – deliverable will be relevant to the whole business

Mark – civil engineer, resource manager. Water have 400 people across the UK, 200 in Cambridge. Environment division are half of that size. 500/600 in the Cambridge office

Informal development program called Sapphire

Research, practices and other companies and academic material. Which way should Mott go in the future?

- Culture of collaboration – is this possible virtually? It has been or will that continue

- Set out different pathways and how each might operate

- Mark mentioned goldman and 3 different paths

  - Focus on the UK

  - Explore the question as a principle

  - Keep it as a study about the principles of the future, then let Mott apply that to their nuanced business units

  - Focus groups from different units will give a range of maturity of opinions as W&E had already implemented “cloud-based secure mobile IT infrastructure”

- Been in place for 2/3 years now. Skype, MS teams, partner arrangement with Microsoft.

- Some parts of business had to stay in person e.g. drawing

- Utilization has been higher (less discretionary activity, more money and business)

- Actually giving more hours to the company – individual suffers as they give their commute time to the company

- Sustainability should form part of the analysis. Business has strategic objective of net-zero carbon – but it just passes carbon to homes.

- Need decision-making criteria to choose desk blend. Criteria of culture and diversity are first tier,sustainability might be second tier. Efficiency is important so is cost

- Environmental economic and people = sustainability

- Open to a blindingly obvious singular recommendation but also open to exploration of different scenarios and their pros and cons for Mott to make a nuanced decision. Mark wants options and a discussion of potential pathways, and also our recommendation of our opinion on the best pathway.

  - Client’s decision may be based on more factors that we can consider plus political elements

  - Lay out the facts and recommend but state assumptions of recommendation.

Don’t make the final recommendation until you see the political issues. Test the water and consult

- 40 grads have joined since Covid.

- Fine to employ a range of potential office for future of varying degrees of innovation.

- Sal has worked remotely for a while. Sal lost visibility amongst people in the office. Could this be a problem with the blended approach?

- How many desks do we need per person? Core question. Design principles are important, not the physical design itself. What space do we need to provide (ratio) and how could that look. Design less important.

- Mark is the point of contact for organizing interviews. Early career professionals (graduates in their first five years). Cross section by seniority and business unit.

Branding and culture

- Develop on the surveys used